## John Ayad
Story ID
PT-00
TC Structure |  |  |  |  | Testing Round 1 (Android) Staging |  |  |  |  | Testing Round 1 (IOS) Staging |  |  |  |  | Testing Round 2 (Android) Staging |  |  |  |  | Testing Round 2 (IOS) Staging
ID | Title | Pre.conditions | Steps | Expected results | Status | Tester Name | Date | Bugs | Comments | Status | Tester Name | Date | Bugs | Comments | Status | Tester Name | Date | Bugs | Comments | Status | Tester Name | Date | Bugs | Comments
PT-01 | Open Markets Overview | log out | 1-open the website 2-log out 3-click on market | 1-market will open without any problem 2-The system should display a table containing: Coin Name, Last Price, 24h Change, and a Sparkline chart | Passed | John Ayad | 25/3/2026 | NA | NA
PT-02 | Live Price Update Data | User is on the Markets page. | 1. Monitor the "Last Price" column for 30 seconds. | 1. Prices must update in real-time. | Passed | John Ayad | 25/3/2026 | NA | NA
PT-03 | Search Functionality | Markets page is loaded. | 1. Type "BTC" in the search box. 2. Observe the filtered list. | 1. Only Bitcoin (BTC) pairs are displayed. | Passed | John Ayad | 25/3/2026 | NA | NA
PT-04 | Invalid Search Input | Markets page is loaded. | 1. Type special characters like "@#$%" in search. | 1. "No results found" message is displayed. 2. No system crash occurs. | Passed | John Ayad | 25/3/2026 | NA | NA
PT-05 | Sorting by 24h Change | Market table is displayed. | 1. Click on "24h Change " header. 2. Click it again. | 1. First click: Descending order. 2. Second click: Ascending order. | Passed | John Ayad | 25/3/2026 | NA | NA
PT-06 | Market Category Tabs | User is on Markets page. | 1. Click on "Spot" tab. 2. Click on "Futures" tab. | 1. Content switches correctly between Spot and Futures markets. | Passed | John Ayad | 25/3/2026 | NA | NA
PT-07 | Add to Favorites (Guest) | User is NOT logged in. | 1. Click on the "Star" icon next to any coin. | 1. System redirects user to Login page or shows a login popup. | Passed | John Ayad | 25/3/2026 | NA | NA
PT-08 | Coin Detail Redirection | Market table is displayed. | 1. Click on the name of any coin (e.g., ETH). | 1. User is redirected to the Trading/Chart page of that specific coin. | Passed | John Ayad | 25/3/2026 | NA | NA
PT-09 | Pagination System | Table footer is visible. | 1. Scroll to the bottom. 2. Click on page "2". | 1. New set of assets loads correctly. 2. Page number "2" is highlighted. | Passed | John Ayad | 25/3/2026 | NA | NA
PT-10 | Change Currency View | Markets page is loaded. | 1. Click on Currency selector. 2. Change from USD to EUR. | 1. All prices in the table are converted to EUR with (€) symbol. | Passed | John Ayad | 25/3/2026 | NA | NA
PT-11 | Open Futures Market | User is on Markets page. | 1. Click on "Futures" tab. | 1. Futures market opens successfully. | Passed | John Ayad | 2026-11-05 | NA | NA
PT-12 | Open Spot Market | User is on Futures tab. | 1. Click on "Spot" tab. | 1. Spot market opens successfully. | Passed | John Ayad | 2026-11-05 | NA | NA
PT-13 | Open Coin From Search Result | Search results are displayed. | 1. Click on searched coin. 2.search for coin 3.click on it | 1. Correct coin page opens. | Passed | John Ayad | 2026-11-05 | NA | NA
PT-14 | Open User Dashboard | User is logged in. | 1. Click on profile icon. 2. Click on "Dashboard". | 1. Dashboard page opens successfully. | Passed | John Ayad | 2026-11-05 | NA | NA
PT-15 | Verify User Information Display | User is on Dashboard page. | 1. Observe account information section | 1. User information is displayed correctly | Passed | John Ayad | 2026-11-05 | NA | NA
PT-16 | Verify Currency Values | User is on Dashboard page. | 1. Observe displayed currency values. | 1. Values are displayed correctly without errors. | Passed | John Ayad | 2026-11-05 | NA | NA
PT-17 | Open Margin Assets Page | User is logged in. | 1.Click profile/assets icon. 2. Click "Assets". 3. Click "Margin | 1. Margin page opens successfully. | Passed | John Ayad | 2026-11-05 | NA | NA
PT-18 | Verify Profit and Loss Display | User is on Margin page. | 1. Observe PnL section. | 1. Profit and loss values are displayed correctly. | Passed | John Ayad | 2026-11-05 | NA | NA
PT-19 | Open Orders Page | User is logged in. | 1. Click profile icon 2. Click Orders | 1. Orders page opens successfully | Passed | John Ayad | 2026-11-05 | NA | NA
PT-20 | Verify Trade History Display | User has past trades. | 1. Open Trade History | 1. All past trades are displayed correctly | Passed | John Ayad | 2026-11-05 | NA | NA
PT-21 | Filter Orders by Date | User is on Order History page. | 1. Select date filter 2. Apply filter | 1. Only orders in selected date appear | Passed | John Ayad | 2026-11-05 | NA | NA

## Lobna Mohamed
Story ID
PT-00
TC Structure |  |  |  |  | Testing Round 1 (Android) Staging |  |  |  |  | Testing Round 1 (IOS) Staging |  |  |  |  | Testing Round 2 (Android) Staging |  |  |  |  | Testing Round 2 (IOS) Staging
ID | Title | Pre.conditions | Steps | Expected results | Status | Tester Name | Date | Bugs | Comments | Status | Tester Name | Date | Bugs | Comments | Status | Tester Name | Date | Bugs | Comments | Status | Tester Name | Date | Bugs | Comments
PT-01 | Open Futures Page | Internet connection available | 1- Open Binance website 2- Click on "Futures" 3- Select "USD-M Futures" | Futures page opens successfully | Passed | Lobna Mohamed | 26/3/2026 | NA | NA
PT-02 | View Chart | Futures page opened | Locate chart section | Chart is displayed | Passed | Lobna Mohamed | 26/3/2026 | NA | NA
PT-03 | Hover on Chart | Chart is visible | Move mouse over the chart | Price and time data change dynamically | Passed | Lobna Mohamed | 26/3/2026 | NA | NA
PT-04 | Buy Order | Futures page is opened | 1- Enter valid price 2- Enter valid amount 3- Click on "Buy" | Order is processed successfully | Passed | Lobna Mohamed | 26/3/2026 | NA | NA
PT-05 | Sell Order | Futures page is opened | 1- Enter valid price 2- Enter valid amount 3- Click on "Sell" | Order is processed successfully | Passed | Lobna Mohamed | 26/3/2026 | NA | NA
PT-06 | Invalid Input | Futures page is opened | 1- Enter invalid data 2- Click on "Buy" | Error message appears | Passed | Lobna Mohamed | 26/3/2026 | NA | NA
PT-07 | View Order Book | Futures page is opened | Locate order book section | Order book is displayed with prices and quantities | Passed | Lobna Mohamed | 26/3/2026 | NA | NA
PT-08 | Real-time Update | Futures page is opened | Wait for a few seconds | Prices update automatically in real-time | Passed | Lobna Mohamed | 26/3/2026 | NA | NA
PT-09 | Change Time Frame | Futures page is opened | 1- Click on time options (1m / 5m / 1H / 1D) 2- Select a different time frame | Chart updates according to selected time frame | Passed | Lobna Mohamed | 26/3/2026 | NA | NA
PT-10 | Switch Between Tabs | Futures page is opened | 1- Click on "Chart" 2- Click on "Info" or "Trading Data" | Displayed content changes correctly | Passed | Lobna Mohamed | 26/3/2026 | NA | NA
PT-11 | View Open Orders | Futures page is opened | 1- Open Open Orders section 2- View the available open orders 3- Check order details | Open Orders are displayed successfully with correct details | Passed | Lobna Mohamed | 25/6/2026 | NA | NA
PT-12 | Verify Open Order Details | Futures page is opened | Open Open Orders section 2- View the available open orders 3- Check order details | Order price, quantity, and status are displayed correctly. | Passed | Lobna Mohamed | 25/6/2026 | NA | NA
PT-13 | Cancel Open Order | Futures page is opened | 1- Open Open Orders section 2- Select an order 3- Click on Cancel Order 4- Confirm cancellation | Order is cancelled successfully and removed from Open Orders | Passed | Lobna Mohamed | 25/6/2026 | NA | NA
PT-14 | View Position Details | Active position exists | 1- Open Positions section 2- Select the active position 3- Review position details | Order is cancelled successfully and removed from Open Orders | Passed | Lobna Mohamed | 25/6/2026 | NA | NA
PT-15 | Verify Profit/Loss | Active position exists | 1- Open Positions section 2- Observe Profit/Loss value 3- Wait for market update | Profit/Loss value updates correctly. | Passed | Lobna Mohamed | 25/6/2026 | NA | NA
PT-16 | Set Take Profit | Active position exists. | 1- Open position settings 2- Enter a valid Take Profit value 3- Click Save | Take Profit value is saved successfully. | Passed | Lobna Mohamed | 25/6/2026 | NA | NA
PT-17 | Set Stop Loss | Active position exists. | 1- Open position settings 2- Enter a valid Stop Loss value 3- Click Save | Stop Loss value is saved successfully | Passed | Lobna Mohamed | 25/6/2026 | NA | NA
PT-18 | Invalid TP/SL Input | Active position exists. | 1- Open TP/SL settings 2- Enter an invalid value 3- Click Save | Validation message appears and invalid value is rejected | Passed | Lobna Mohamed | 25/6/2026 | NA | NA
PT-19 | Modify Open Order | Open order exists | 1- Open Open Orders section 2- Select an order 3- Modify the order value 4- Save changes | Order is updated successfully | Passed | Lobna Mohamed | 25/6/2026 | NA | NA
PT-20 | Close Position | Active position exists | 1- Open Positions section 2- Select the active position 3- Click Close Position 4- Confirm the action | Position is closed successfully | Passed | Lobna Mohamed | 25/6/2026 | NA | NA

## Logeen Mohammed
Story ID
PT-00
TC Structure |  |  |  |  | Testing Round 1 (Android) Staging |  |  |  |  | Testing Round 1 (IOS) Staging |  |  |  |  | Testing Round 2 (Android) Staging |  |  |  |  | Testing Round 2 (IOS) Staging
ID | Title | Pre.conditions | Steps | Expected results | Status | Tester Name | Date | Bugs | Comments | Status | Tester Name | Date | Bugs | Comments | Status | Tester Name | Date | Bugs | Comments | Status | Tester Name | Date | Bugs | Comments
PT-01 | Verify Earn page loads | User logged in | Open Earn page | Page loads successfully and displays dashboard | Passed | Logeen Mohammed | 26/3/2026 | NA | NA
PT-02 | Verify My Holdings display | User logged in | Open Earn page | My Holdings is displayed (even if 0.00) | Passed | Logeen Mohammed | 26/3/2026 | NA | NA
PT-03 | Verify Total Profit display | User logged in | Open Earn page | Total Profit is displayed correctly | Passed | Logeen Mohammed | 26/3/2026 | NA | NA
PT-04 | Verify Last Day Profit display | User logged in | Open Earn page | Last Day Profit is displayed correctly | Passed | Logeen Mohammed | 26/3/2026 | NA | NA
PT-05 | Verify navigation between tabs | User logged in | Click Overview Click Simple Earn Click Advanced Earn | Each tab opens its corresponding page | Passed | Logeen Mohammed | 26/3/2026 | NA | NA
PT-06 | Verify Deposit button | User logged in | Click Deposit button | User is redirected to deposit page | Passed | Logeen Mohammed | 26/3/2026 | NA | NA
PT-07 | Verify "What is Earn" link | User logged in | Click "What is Earn?" | Info popup or page is displayed | Passed | Logeen Mohammed | 26/3/2026 | NA | NA
PT-08 | Verify banner display | User logged in | Open Earn page | Banner appears correctly without UI issues | Passed | Logeen Mohammed | 26/3/2026 | NA | NA
PT-09 | Verify zero balance state | User has no funds | Open Earn page | All values show 0.00 without errors | Passed | Logeen Mohammed | 26/3/2026 | NA | NA
PT-10 | Verify behavior with no internet | Internet disconnected | Open Earn page | Error message appears or page doesn’t crash | Passed | Logeen Mohammed | 26/3/2026 | NA | NA
PT-11 | verifiy cofirmation popup | Valid subscription | Click Subscribe | Confirmation popup appears with details | Passed | Logeen Mohammed | 2026-01-05 | NA | NA
PT-12 | enable auto - subscription | Active subscription | Toggle Auto-Subscribe ON | Feature enabled successfully | Passed | Logeen Mohammed | 2026-01-05 | NA | NA
PT-13 | reedem flexible product | Active flexible subscription | Click Redeem | Funds returned instantly | Passed | Logeen Mohammed | 2026-01-05 | NA | NA
PT-14 | redeem locked product early | Locked product active | Click Redeem early | Warning displayed + penalty applied | Passed | Logeen Mohammed | 2026-01-05 | NA | NA
PT-15 | verify APR display | Earn page loaded | Observe APR values | APR displayed correctly | Passed | Logeen Mohammed | 2026-01-05 | NA | NA
PT-16 | sort by APR | Product list visible | Sort by APR | Products sorted descending | Passed | Logeen Mohammed | 2026-01-05 | NA | NA
PT-17 | empty search result | open Earn page | Search random coin | "No results found" displayed | Passed | Logeen Mohammed | 2026-01-05 | NA | NA
PT-18 | risk disclaimer | Product details page | Open any product | Risk warning visible | Passed | Logeen Mohammed | 2026-01-05 | NA | NA
PT-19 | logout and access restriction | User logged out | Try accessing Earn | Redirect to login | Passed | Logeen Mohammed | 2026-01-05 | NA | NA

## Ahmed Saleh
Story ID
PT-00
TC Structure |  |  |  |  | Testing Round 1 (Android) Staging |  |  |  |  | Testing Round 1 (IOS) Staging |  |  |  |  | Testing Round 2 (Android) Staging |  |  |  |  | Testing Round 2 (IOS) Staging
ID | Title | Pre.conditions | Steps | Expected results | Status | Tester Name | Date | Bugs | Comments | Status | Tester Name | Date | Bugs | Comments | Status | Tester Name | Date | Bugs | Comments | Status | Tester Name | Date | Bugs | Comments
PT-01 | Open Homepage | Internet connection is available | 1- Open browser (e.g., Chrome) 2- Enter website URL: https://www.binance.com/en 3- Press Enter | 1- Homepage loads successfully 2- No errors are displayed 3-Page content appears correctly | Passed | Ahmed Saleh | 20/3/2026 | NA | NA |  | Wait |  |  |  |  | Wait |  |  |  |  | Wait
PT-02 | Verify Homepage UI Elements | Homepage is opened | 1- Check website logo 2- Check navigation bar 3- Check "Sign Up" and "Log In" buttons | 1- Logo is visible and correctly placed 2- Navigation bar is displayed 3- "Sign Up" and "Log In" buttons are visible and clickable | Passed | Ahmed Saleh | 20/3/2026 | NA | NA |  | Wait |  |  |  |  | Wait |  |  |  |  | Wait
PT-03 | Navigate to Sign Up Page | User is not logged in | Click on "Sign Up" button | 1-User is redirected to the registration page 2-Registration form is displayed | Passed | Ahmed Saleh | 20/3/2026 | NA | NA |  | Wait |  |  |  |  | Wait |  |  |  |  | Wait
PT-04 | Navigate to Login Page | User has an existing account | Click on "Log In" button | 1- User is redirected to login page 2- Login form is displayed | Passed | Ahmed Saleh | 20/3/2026 | NA | NA |  | Wait |  |  |  |  | Wait |  |  |  |  | Wait
PT-05 | Login with Valid Credentials | User is registered | 1- Navigate to login page 2- Enter valid email (e.g., test@gmail.com) 3- Enter valid password (e.g., Test@1234) 4-Click on "Log In" | 1- User is successfully authenticated 2- User is redirected to dashboard 3- User account name is displayed 4- No error messages appear | Passed | Ahmed Saleh | 20/3/2026 | NA | NA |  | Wait |  |  |  |  | Wait |  |  |  |  | Wait
PT-06 | Login with Invalid Password | User is registered | 1- Navigate to login page 2- Enter valid email (e.g., test@gmail.com) 3- Enter invalid password (e.g., 123456) 4- Click on "Log In" | 1- Error message "Invalid email or password" is displayed 2- User remains on login page 3- Login is not successful | Passed | Ahmed Saleh | 20/3/2026 | NA | NA |  | Wait |  |  |  |  | Wait |  |  |  |  | Wait
PT-07 | View Cryptocurrency Prices | Homepage is opened | 1- Scroll down the homepage 2- Locate cryptocurrency list | 1- List of cryptocurrencies is displayed Each item shows: 1- Coin name 2- Current price 3- Percentage change 4-Data is loaded without errors | Passed | Ahmed Saleh | 20/3/2026 | NA | NA |  | Wait |  |  |  |  | Wait |  |  |  |  | Wait
PT-08 | Navigate to Cryptocurrency Details | Homepage is opened | Click on any cryptocurrency (e.g., BTC/USDT) | 1- User is redirected to coin details page 2- Detailed information about the selected coin is displayed | Passed | Ahmed Saleh | 21/3/2026 | NA | NA |  | Wait |  |  |  |  | Wait |  |  |  |  | Wait
PT-09 | Navigate to Trade Page | Homepage is opened | Click on "Trade" from navigation bar | 1- User is redirected to trading page 2-Trading interface is displayed correctly | Passed | Ahmed Saleh | 21/3/2026 | NA | NA |  | Wait |  |  |  |  | Wait |  |  |  |  | Wait
PT-10 | Navigate to Download App Page | Homepage is opened | Click on "Download" button | 1- User is redirected to app download page 2- Download options (Android / iOS) are displayed | Passed | Ahmed Saleh | 21/3/2026 | NA | NA |  | Wait |  |  |  |  | Wait |  |  |  |  | Wait
PT-11 | Open Buy Crypto Page | Internet connection available | 1- Open Binance 2- Click "Buy Crypto | 1- Page loads successfully 2- No UI issues | Passed | Ahmed Saleh | 2026-01-05 | NA | NA |  | Wait
PT-12 | Select Fiat Currency | User on Buy Crypto page | 1- Click fiat dropdown 2- Select EGP | 1- Currency updates correctly 2- Values refresh | Passed | Ahmed Saleh | 2026-01-05 | NA | NA |  | Wait
PT-13 | Select Cryptocurrency | User on Buy Crypto page | 1- Click crypto dropdown 2- Select BTC | 1- BTC is selected 2- UI updates | Passed | Ahmed Saleh | 2026-01-05 | NA | NA |  | Wait
PT-14 | Enter Valid Amount | User on Buy Crypto page | 1- Enter 1000 EGP | 1- Equivalent BTC is calculated 2- No errors | Passed | Ahmed Saleh | 2026-01-05 | NA | NA |  | Wait
PT-15 | Real-time Conversion | User entered amount | 1- Change amount from 1000 → 2000 | 1- Conversion updates instantly | Passed | Ahmed Saleh | 2026-01-05 | NA | NA |  | Wait
PT-16 | Select Payment Method | User on Buy Crypto page | 1- Choose "Card" 2- Switch to "P2P" | 1- Payment method switches correctly | Passed | Ahmed Saleh | 2026-01-05 | NA | NA |  | Wait
PT-17 | Proceed to Payment | User entered valid data | 1- Click "Buy BTC" | 1- Redirect to payment page 2- Summary displayed | Passed | Ahmed Saleh | 2026-01-05 | NA | NA |  | Wait
PT-18 | Successful Payment | User has valid card | 1- Enter card details 2- Confirm payment | 1- Transaction successful 2- Crypto added to wallet | Passed | Ahmed Saleh | 2026-01-05 | NA | NA |  | Wait
PT-19 | Payment Failure | User has invalid card | 1- Enter wrong card info 2- Confirm | 1- Error message displayed 2- No deduction | Passed | Ahmed Saleh | 2026-01-05 | NA | NA |  | Wait
PT-20 | Negative Amount Validation | User on Buy page | 1- Enter -100 | 1- Error shown 2- Input rejected | Passed | Ahmed Saleh | 2026-01-05 | NA | NA |  | Wait
PT-21 | Non-numeric Input | User on Buy page | 1- Enter "abc" | 1- Field rejects input | Passed | Ahmed Saleh | 2026-01-05 | NA | NA |  | Wait
PT-22 | Minimum Limit Validation | User on Buy page | 1- Enter very small amount | 1- Error: below minimum limit | Passed | Ahmed Saleh | 2026-01-05 | NA | NA |  | Wait
PT-23 | Maximum Limit Validation | User on Buy page | 1- Enter huge amount | 1- Error: exceeds limit | Passed | Ahmed Saleh | 2026-01-05 | NA | NA |  | Wait
PT-24 | Empty Fields | Submission User on Buy page | 1- Leave fields empty 2- Click Buy | 1- Validation errors shown | Passed | Ahmed Saleh | 2026-01-05 | NA | NA |  | Wait

## Kareem Adel
Story ID
PT-00
TC Structure |  |  |  |  | Testing Round 1 (Android) Staging |  |  |  |  | Testing Round 1 (IOS) Staging |  |  |  |  | Testing Round 2 (Android) Staging |  |  |  |  | Testing Round 2 (IOS) Staging
ID | Title | Pre.conditions | Steps | Expected results | Status | Tester Name | Date | Bugs | Comments | Status | Tester Name | Date | Bugs | Comments | Status | Tester Name | Date | Bugs | Comments | Status | Tester Name | Date | Bugs | Comments
PT-01 | Market Buy Order – Successful Execution | User is logged in User has sufficient USDT balance BTC/USDT trading pair is available | 1. Navigate to Trade → Spot 2. Select BTC/USDT pair 3. Choose "Market" order type 4. Enter amount = 0.001 BTC 5. Click "Buy BTC" 6. Confirm order | Order executes instantly BTC balance increases (~0.001 BTC minus fees) USDT balance decreases accordingly Order status = "Filled" in Order History | Passed | Kareem Adel | 26/3/2026 | NA | NA
PT-02 | Limit Buy Order – Pending Execution | User logged in Sufficient USDT balance available | 1. Navigate to Spot Trading 2. Select BTC/USDT 3. Choose "Limit" order 4. Enter price lower than market price 5. Enter quantity = 0.001 6. Click "Buy BTC" | Order is placed successfully Status = "Open" Appears in Open Orders tab Not executed immediately | Passed | Kareem Adel | 26/3/2026 | NA | NA
PT-03 | Cancel Open Limit Order | User logged in At least one open order exists | 1. Navigate to Open Orders 2. Locate active order 3. Click "Cancel" 4. Confirm cancellation | Order removed from Open Orders Status updated to "Cancelled" Reserved funds returned to balance | Passed | Kareem Adel | 26/3/2026 | NA | NA
PT-04 | Market Sell Order – Full Balance | User logged in User owns BTC | 1. Go to BTC/USDT Spot 2. Select Market Sell 3. Click "100%" 4. Confirm order | Order executed immediately BTC balance becomes ~0 USDT balance increases Order status = "Filled" | Passed | Kareem Adel | 26/3/2026 | NA | NA
PT-05 | Market Buy – Insufficient Balance | User logged in User balance = 0 USDT | 1. Navigate to Spot BTC/USDT 2. Enter quantity requiring 500 USDT 3. Click "Buy BTC" | Error message displayed: "Insufficient balance" Order is NOT placed No changes in balances | Passed | Kareem Adel | 26/3/2026 | NA | NA
PT-06 | Limit Order – Negative Price Validation | User logged in | 1. Navigate to Spot trading 2. Select Limit order 3. Enter price = -5000 4. Click Buy | Validation error appears Message: "Price must be greater than 0" Order not submitted | Passed | Kareem Adel | 26/3/2026 | NA | NA
PT-07 | Limit Order – Non-Numeric Price Input | User on trading page | 1. Click price input field 2. Enter "abc" 3. Click Buy | Field rejects input OR auto-clears invalid characters Order submission is blocked | Passed | Kareem Adel | 26/3/2026 | NA | NA
PT-08 | Minimum Order Size – Boundary Valid Case | User has sufficient balance Minimum order value known | 1. Enter minimum quantity 2. Submit Market Buy | Order is accepted Executed successfully No validation errors | Passed | Kareem Adel | 26/3/2026 | NA | NA
PT-09 | Order Quantity Below Minimum | User has balance | 1. Enter quantity below minimum 2. Click Buy | Error message displayed "Minimum order is X BTC" Order not placed | Passed | Kareem Adel | 26/3/2026 | NA | NA
PT-10 | Price Precision Validation | User on Limit order form | 1. Enter price with excessive decimals 2. Submit order | System truncates OR rejects value Validation message shown if invalid Order not submitted with invalid precision | Passed | Kareem Adel | 26/3/2026 | NA | NA
PT-11 | Order Placement Without Authentication | User is logged out | 1. Navigate directly to trading URL 2. Attempt to place order | Redirect to login page No order executed | Passed | Kareem Adel | 26/3/2026 | NA | NA
PT-12 | Network Timeout Handling | User ready to submit order | 1. Simulate slow network / disconnect 2. Submit order | Error message shown: "Request timed out" No duplicate order created User can retry safely | Passed | Kareem Adel | 26/3/2026 | NA | NA

## Ahmed Anwer
Story ID
PT-00
TC Structure |  |  |  |  | Testing Round 1 (Android) Staging |  |  |  |  | Testing Round 1 (IOS) Staging |  |  |  |  | Testing Round 2 (Android) Staging |  |  |  |  | Testing Round 2 (IOS) Staging
ID | Title | Pre.conditions | Steps | Expected results | Status | Tester Name | Date | Bugs | Comments | Status | Tester Name | Date | Bugs | Comments | Status | Tester Name | Date | Bugs | Comments | Status | Tester Name | Date | Bugs | Comments
PT-01 | Filter ads using "Vodafone Cash" | User is on the P2P "Buy" tab | 1. Click on the "All payment methods" dropdown. 2.Select "Vodafone cash" | Only advertisers who accept Vodafone Cash should appear in the list. | Passed | Ahmed Anwer | 26/3/2026 | NA | NA
PT-02 | Filter ads by specific EGP amount. | User is on the P2P page | 1.Enter "500" in the "Transaction amount" field. 2.Click the Search (magnifying glass) icon. | Only ads with a "Limit" range that includes 500 EGP (e.g., 90.00 EGP - 7,965.00 EGP) should be displayed. | Passed | Ahmed Anwer | 26/3/2026 | NA | NA
PT-03 | Navigation between Buy and Sell modes | User is on the P2P page. | 1.Click on the "Sell" toggle button next to "Buy". | The button colors change (Sell usually red), and the list updates to show "Sell" advertisements. | Passed | Ahmed Anwer | 26/3/2026 | NA | NA
PT-04 | Switch asset from USDT to BTC | Default asset is USDT. | 1.Click on "BTC" in the asset navigation bar | The price column changes to reflect BTC prices in EGP, and "Buy BTC" buttons appear. | Passed | Ahmed Anwer | 26/3/2026 | NA | NA
PT-05 | Display of advertiser statistics | Ads are loaded on the page. | 1.Observe the info under the advertiser's name (e.g., FOX-DIGITAL-GATE). | Data like "1998 orders" and "97.20% completion" must be clearly visible. | Passed | Ahmed Anwer | 26/3/2026 | NA | NA
PT-06 | Visibility of the "How P2P Works" section | User scrolls down on the P2P landing page | 1.Scroll to the "How P2P Works" section | Three steps (1. Place an Order, 2. Pay the Seller, 3. Receive Crypto) must be displayed with icons. | Passed | Ahmed Anwer | 26/3/2026 | NA | NA
PT-07 | Triggering the Buy Order form. | User is logged in | 1."Buy USDT" button for a specific ad | A pop-up or new page opens showing the payment window and time limit (e.g., 15 min). | Passed | Ahmed Anwer | 26/3/2026 | NA | NA
PT-08 | Accessibility of support resources. | User is on the P2P page. | 1.Click on "P2P Help Center" in the top right. | User is redirected to the Binance Support/FAQ page for P2P. | Passed | Ahmed Anwer | 26/3/2026 | NA | NA
PT-09 | Navigate through multiple pages of ads. | More than one page of ads is available. | 1.Scroll to the bottom of the ad list. 2.Click on page number "2" or the ">" arrow. | The list refreshes to show the next set of advertisers. | Passed | Ahmed Anwer | 26/3/2026 | NA | NA
PT-10 | Quick selection of payment methods from footer. | User scrolls to the "Top Payment Methods" section. | 1.Click on the "InstaPay" box. | The page should automatically filter the P2P ad list to show only InstaPay ads. | Passed | Ahmed Anwer | 26/3/2026 | NA | NA

## Nouran Mohamed
Story ID
PT-00
TC Structure |  |  |  |  | Testing Round 1 (Android) Staging |  |  |  |  | Testing Round 1 (IOS) Staging |  |  |  |  | Testing Round 2 (Android) Staging |  |  |  |  | Testing Round 2 (IOS) Staging
ID | Title | Pre.conditions | Steps | Expected results | Status | Tester Name | Date | Bugs | Comments | Status | Tester Name | Date | Bugs | Comments | Status | Tester Name | Date | Bugs | Comments | Status | Tester Name | Date | Bugs | Comments
PT-01 | Checking Feed Loading and Content Display | - User is logged in - Stable internet connection | Open the "Square" tab from the homepage | - Feed loads without delay or errors. - Creator names, post content, timestamps, and interaction buttons are visible. | Passed | Nouran Mohamed | 26/03/2026 | NA | NA
PT-02 | Checking Searching by Cashtag | User is on the Square page | - Enter "$ETH" in the search bar - Press Enter | - Results update dynamically - Only posts containing "$ETH" are shown - No irrelevant posts appear | Passed | Nouran Mohamed | 26/03/2026 | NA | NA
PT-03 | Checking Sorting Criteria (Hot / Latest) | - Posts are already displayed | - Switch between "Hot" and "Latest" | - Posts reorder instantly "Latest" shows newest posts first - No duplication or missing posts | Passed | Nouran Mohamed | 26/03/2026 | NA | NA
PT-04 | Checking Cashtag Redirection | A post includes "$BNB" | Click on "$BNB" in the post | - Navigation happens smoothly - Correct trading page opens - No broken links or errors | Passed | Nouran Mohamed | 26/03/2026 | NA | NA
PT-05 | Checking Follow Functionality | User is not following the creator | Click "Follow" | - Button toggles to "Following" - No delay or UI glitch - Creator’s posts start appearing in Following tab | Passed | Nouran Mohamed | 26/03/2026 | NA | NA
PT-06 | Checking Commenting on a Post | User has a verified account | - Open comments - Add a comment - Send | - Comment appears instantly - Counter updates correctly - No duplicate or missing comments | Passed | Nouran Mohamed | 26/03/2026 | NA | NA
PT-07 | Checking Translation in app | Post is in a different language | - Click "choose language"./ -Click "Autotranslation". | - Translation appears quickly. - Text is readable. | Passed | Nouran Mohamed | 26/03/2026 | NA | NA
PT-08 | Checking Post Sharing | - User is logged in/ -User is viewing a post in Square page | - Click "Share" - Choose "Copy Link" | - Confirmation message appears - Link works when opened externally - Opens the correct post. | Passed | Nouran Mohamed | 26/03/2026 | NA | NA
PT-09 | Checking Infinite Scroll | User scrolls near the end of the feed | Continue scrolling | - More content loads smoothly - No freezing or repeated posts - Loading indicator behaves correctly | Passed | Nouran Mohamed | 26/03/2026 | NA | NA
PT-10 | Checking Tipping Feature | - Tipping is enabled - User has enough balance | - Click "Tip" - Enter amount - Confirm | - Transaction completes without error - Balance updates correctly - Confirmation message appears | Passed | Nouran Mohamed | 26/03/2026 | NA | NA
PT-11 | Checking Search functionality with keywords | - User is logged in / - User using search bar in square page | 1. Enter "Binance News" in the search bar. 2. Click "Search". | 1. Display list of posts related to the word in search bar. | Passed | Nouran Mohamed | 2026-01-05 | NA | NA
PT-12 | Checking Interaction with posts (Liket) | - user is logged in / user is in the square page viewing a Post. | 1. Click the (Like) icon on a post. | 1. Icon changes color (yellow). 2. Like count increases immediately without page refresh. | Passed | Nouran Mohamed | 2026-01-05 | NA | NA
PT-13 | Checking Image Upload in Post | 1.User is logged in. 2. Account has "Creator" permissions. | 1. Click "Create Post". 2. Click image icon and select a JPG file. 3. Click "Publish" | Post is published successfully with the image displayed. | Passed | Nouran Mohamed | 2026-01-05 | NA | NA
PT-14 | Report Inappropriate Content. | 1. User is logged in. 2. Viewing a post by another user. | 1. Click the "Three Dots" menu on a post. 2. Select "Report". 3. Choose a reason and click "Submit". | A confirmation message "Report Submitted" appears. | Passed | Nouran Mohamed | 2026-01-05 | NA | NA
PT-15 | Bookmark/Save Post | 1. User is logged in. 2. User is on the Square feed. | 1. Click the "Bookmark" icon on a post. 2. Navigate to "My Bookmarks" in profile. | The saved post appears in the Bookmarks list. | Passed | Nouran Mohamed | 2026-01-05 | NA | NA
PT-16 | Tagging User. | 1. User is in the "Create Post" window. | 1. Type "@" followed by "Binance". 2. Select the official account from the list. | The mention is highlighted and becomes a clickable link after publishing. | Passed | Nouran Mohamed | 2026-01-05 | NA | NA
PT-17 | Filter Feed by Category. | 1. User is on the Square homepage. | 1. Click on the "News" tab at the top. 2. Scroll through the results. | Only content tagged as "News" is displayed on the screen. | Passed | Nouran Mohamed | 2026-01-05 | NA | NA
PT-18 | Voting in User Polls. | 1. A post with an active poll is visible. | 1. Select one of the poll options. 2. Click "Vote". | The percentage bars update to show the current poll results. | Passed | Nouran Mohamed | 2026-01-05 | NA | NA
PT-19 | Search by Keyword. | 1. User is logged in. 2. Internet connection is stable. | 1. Click search icon. 2. Type "any word" and press Enter. | Feed filters to show only posts containing the keyword "any word". | Passed | Nouran Mohamed | 2026-01-05 | NA | NA
PT-20 | Copy Post Link for Sharing. | 1. User is viewing a specific post. | 1. Click the "Share" icon. 2. Click "Copy Link". | Link Copied" as message appears; URL is saved to clipboard. | Passed | Nouran Mohamed | 2026-01-05 | NA | NA